## Sheet1
Project Title
Agile Story Id | Agile Story Title | Tasks | Estimated Hrs | Student Name | Start Date | End Date
Agile Story 1 | Login to FRS | Designing the page to enter login id and password | 1 | K Misra | 2022-05-03 | 2022-05-04
|  | testing the page | 1 | K Misra | 2022-05-05 | 2022-05-06
|  | bug fixing | 1 | K Misra | 2022-05-07 | 2022-05-07
Agile Story 2 | Searching of the flight | Designing the page so that the user could search for flights | 4 | S Kaur | 2022-05-03 | 2022-05-04
|  | entering the date of flying as well as the origin and destination city the person is flying | 5 | S Kaur | 2022-05-03 | 2022-05-04
|  | entering the data of flight of 5 cities(for now) | 3 | S Kaur | 2022-05-03 | 2022-05-05
|  | Showing flight details | 2 | S Kaur | 2022-05-06 | 2022-05-06
|  | testing the page | 3 | S Kaur | 2022-05-06 | 2022-05-06
|  | bug fixing | 2 | S Kaur | 2022-05-07 | 2022-05-07
Agile Story 3 | Booking of the flight | inputs from person form to add details on the page. | 3 | S Kaur | 2022-05-09 | 2022-05-10
|  | Booking button | 3 | S Kaur | 2022-05-09 | 2022-05-10
|  | testing the story | 3 | S Kaur | 2022-05-11 | 2022-05-12
|  | bug fixing | 2 | S Kaur | 2022-05-11 | 2022-05-12
Agile Story 4 | Confirmation of the flight | The ticket is confirmed here | 2 | K Misra | 2022-05-09 | 2022-05-10
|  | testing the story | 3 | K Misra | 2022-05-09 | 2022-05-10
|  | bug fixing | 2 | K Misra | 2022-05-09 | 2022-05-10
Agile Story 5 | Cancellation of the flight | If the user wants to cancel the flight, he/she can click on the "cancel flight" button | 2 | C Varshney | 2022-05-16 | 2022-05-16
|  | enter the details and click on proceed and then click on confirm cancelation | 3 | C Varshney | 2022-05-16 | 2022-05-16
|  | the cancelled flight page will show up | 1 | C Varshney | 2022-05-16 | 2022-05-16
|  | testing the story | 3 | C Varshney | 2022-05-17 | 2022-05-17
|  | bug fixing | 1 | C Varshney | 2022-05-17 | 2022-05-17
Agile Story 6 | Changing of the flight | If the user wants to change the flight, he/she can click on the "Change flight" button | 2 | C Varshney | 2022-05-18 | 2022-05-19
|  | enter the details and click on proceed and then click on confirm cancelation | 4 | C Varshney | 2022-05-18 | 2022-05-19
|  | the list of the Flights will show up and the user can book a flight as well | 4 | C Varshney | 2022-05-20 | 2022-05-21
|  | the new ticket is displayed | 3 | C Varshney | 2022-05-20 | 2022-05-21
|  | testing the story | 2 | C Varshney | 2022-05-20 | 2022-05-21
|  | bug fixing | 1 | C Varshney | 2022-05-20 | 2022-05-21