## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | C Varshney | 2022-05-02 | 2022-05-21 |  | 95% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Login to FRS - Designing the page to enter login id and password |  | K Misra | 3 | 2022-05-03 | 2022-05-04 | 1 | Complete
| Login to FRS-testing the page |  | K Misra |  | 2022-05-05 | 2022-05-06 | 1 | Complete
| Login to FRS-bug fixing |  | K Misra |  | 2022-05-07 | 2022-05-07 | 1 | Complete
Complete
| Searching of the flight-Designing the page so that the user could search for flights |  | S Kaur | 8 | 2022-05-03 | 2022-05-04 | 1 | Complete
| Searching of the flight-entering the date of flying as well as the origin and destination city the person is flying |  | S Kaur |  | 2022-05-03 | 2022-05-04 | 1 | Complete
| Searching of the flight-entering the data of flight of 5 cities(for now) |  | S Kaur |  | 2022-05-03 | 2022-05-05 | 2 | Complete
| Searching of the flight-Should be able to show the details of each and every flight |  | S Kaur |  | 2022-05-06 | 2022-05-06 | 1 | Complete
| Searching of the flight-testing the page |  | S Kaur |  | 2022-05-06 | 2022-05-06 | 1 | Complete
| Searching of the flight-bug fixing |  | S Kaur |  | 2022-05-07 | 2022-05-07 | 1 | Complete
| Booking of the flight-the person should add his/her details on the page. |  | S Kaur | 5 | 2022-05-09 | 2022-05-10 | 1 | Complete
| Booking of the flight-they should be able to book the flight |  | S Kaur |  | 2022-05-09 | 2022-05-10 | 2 | Complete
| Booking of the flight-testing the story |  | S Kaur |  | 2022-05-11 | 2022-05-12 | 2 | Complete
| Booking of the flight-bug fixing |  | S Kaur |  | 2022-05-11 | 2022-05-12 | 2 | Complete
| Confirmation of the flight-The ticket is confirmed here |  | K Misra | 5 | 2022-05-09 | 2022-05-10 | 2 | Complete
| Confirmation of the flight-testing the story |  | K Misra |  | 2022-05-09 | 2022-05-10 | 2 | Complete
| Confirmation of the flight-bug fixing |  | K Misra |  | 2022-05-09 | 2022-05-10 | 2 | Complete
Complete
| Cancellation of the flight-If the user wants to cancel the flight, he/she can click on the "cancel flight" button |  | C Varshney | 5 | 2022-05-16 | 2022-05-16 | 1 | Complete
| Cancellation of the flight-enter the details and click on proceed and then click on confirm cancelation |  | C Varshney |  | 2022-05-16 | 2022-05-16 | 1 | Complete
| Cancellation of the flight-the cancelled flight page will show up |  | C Varshney |  | 2022-05-16 | 2022-05-16 | 1 | Complete
| Cancellation of the flight-testing the story |  | C Varshney |  | 2022-05-17 | 2022-05-17 | 1 | Complete
| Cancellation of the flight-bug fixing |  | C Varshney |  | 2022-05-17 | 2022-05-17 | 1 | Complete
| Changing of the flight-If the user wants to change the flight, he/she can click on the "Change flight" button |  | C Varshney | 8 | 2022-05-18 | 2022-05-19 | 2 | Complete
| Changing of the flight-enter the details and click on proceed and then click on confirm cancelation |  | C Varshney |  | 2022-05-18 | 2022-05-19 | 2 | Complete
| Changing of the flight-the list of the Flights will show up and the user can book a flight as well |  | C Varshney |  | 2022-05-20 | 2022-05-21 | 2 | Complete
| Changing of the flight-the new ticket is displayed |  | C Varshney |  | 2022-05-20 | 2022-05-21 | 2 | Complete
| Changing of the flight-testing the story |  | C Varshney |  | 2022-05-20 | 2022-05-21 | 2 | Complete
| Changing of the flight-bug fixing |  | C Varshney |  | 2022-05-20 | 2022-05-21 | 2 | Complete
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.