## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
login to the FRS | 3 | K Misra | DONE | 3
Designing the page to enter login id and password |  |  |  | 1 | 0.5 | 0.5
testing the page |  |  |  | 1 |  |  | 0.5 | 0.5
bug fixing |  |  |  | 1 |  |  |  |  | 1
Searching of the flight | 8 | S Kaur | DONE | 29
Designing the page so that the user could search for flights |  |  |  | 4 | 4
entering the date of flying as well as the origin and destination city the person is flying |  |  |  | 5 | 2 | 3
entering the data of flight of 5 cities(for now) |  |  |  | 3 |  | 3
Should be able to show the details of each and every flight |  |  |  | 2 |  |  | 2
testing the story |  |  |  | 3 |  |  |  | 3
bug fixing |  |  |  | 2 |  |  |  |  | 2
Booking of the flight | 5 | S Kaur | DONE | 14
the person should add his/her details on the page. |  |  |  | 3 | 2 | 1
they should be able to book the flight |  |  |  | 3 |  | 2 | 1
testing the story |  |  |  | 3 |  |  | 2 | 1
bug fixing |  |  |  | 2 |  |  |  |  | 2
confirmation of the flight | 5 | K Misra | DONE | 7
The ticket is confirmed |  |  |  | 2 | 1 | 1
testing the story |  |  |  | 3 |  | 2 | 1
bug fixing |  |  |  | 2 |  |  | 1 | 1
Cancellation of the flight | 5 | C Varshney | DONE | 10
If the user wants to cancel the flight, he/she can click on the "cancel flight" button |  |  |  | 2 | 2
enter the details and click on proceed and then click on confirm cancelation |  |  |  | 3 | 1 | 2 |  |  |  |  | ------
the cancelled flight page will show up |  |  |  | 1 |  | 1
testing the story |  |  |  | 3 |  |  | 2 | 1
bug fixing |  |  |  | 1 |  |  |  | 1
Changing the flight | 8 | C Varshney | DONE | 15
If the user wants to change the flight, he/she can click on the "Change flight" button |  |  |  | 2 | 2
enter the details and click on proceed and then click on confirm cancelation |  |  |  | 4 | 2 | 2
the list of the Flights will show up and the user can book a flight as well |  |  |  | 4 |  | 2 | 2
the new ticket is displayed |  |  |  | 3 |  |  | 2 | 1
testing the story |  |  |  | 2 |  |  |  | 2
bug fixing |  |  |  | 1 |  |  |  |  | 1
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.